## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Setup project structure and Springboot server | MUST HAVE | NA | DanushAditya VC | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Implement Account class & repository with balance handling | MUST HAVE | US-01 | DanushAditya VC | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Implement account creation API | MUST HAVE | US-02 | DanushAditya VC | 3- Completed
Sprint 2 | Sprint 2 | US-04 | Implement deposit functionality | MUST HAVE | US-03 | DanushAditya VC | 3- Completed
Sprint 2 | Sprint 2 | US-05 | Implement withdrawal functionality with exception handling | MUST HAVE | US-03 | DanushAditya VC | 3- Completed
Sprint 2 | Sprint 2 | US-06 | Implement transfer functionality between accounts | MUST HAVE | US-04, US-05 | DanushAditya VC | 3- Completed
Sprint 2 | Sprint 2 | US-07 | Add transaction validation and history logging | MUST HAVE | US-04, US-05 | DanushAditya VC | 3- Completed
Sprint 3 | Sprint 3 | US-08 | Implement low balance alert service | SHOULD HAVE | US-02 | DanushAditya VC | 3- Completed
Sprint 3 | Sprint 3 | US-09 | Implement email notification for low balance | SHOULD HAVE | US-08 | DanushAditya VC | 3- Completed
Sprint 4 | Sprint 4 | US-10 | Develop simple frontend UI for account and transactions | COULD HAVE | NA | DanushAditya VC | 3- Completed
Sprint 4 | Sprint 4 | US-11 | Integrate frontend with backend APIs | SHOULD HAVE | US-10, US-03 | DanushAditya VC | 3- Completed
Sprint 4 | Sprint 4 | US-12 | Perform end-to-end testing of complete workflow | SHOULD HAVE | US-11 | DanushAditya VC | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 5 | 7 | 5 | 5 | 6 | 6 | 4 | 5 | 3 | 7 | 3 | 3 | 6 | 10
SPRINT 1 BACKLOG
US-01 | S1-T1 | Create project folder structure | Day 1 | Day 1 | DanushAditya VC | Setup | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | S1-T2 | Configure Springboot Server setup | Day 1 | Day 1 | DanushAditya VC | Setup | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | S1-T3 | Design Account class | Day 2 | Day 2 | DanushAditya VC | Design | Completed | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | S1-T4 | Implement Account repository | Day 2 | Day 2 | DanushAditya VC | Development | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | S1-T5 | Implement account creation API | Day 3 | Day 3 | DanushAditya VC | Development | Completed | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-04 | S2-T1 | Implement deposit functionality | Day 4 | Day 4 | DanushAditya VC | Development | Completed | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | S2-T2 | Implement withdrawal functionality | Day 5 | Day 5 | DanushAditya VC | Development | Completed | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | S2-T3 | Implement transfer between accounts | Day 6 | Day 6 | DanushAditya VC | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | S2-T4 | Transaction validation & history logging | Day 7 | Day 8 | DanushAditya VC | Development | Not Started | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-08 | S3-T1 | Low balance alert service | Day 9 | Day 10 | DanushAditya VC | Development | Not Started | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0
US-09 | S3-T2 | Email notification for low balance | Day 10 | Day 11 | DanushAditya VC | Development | Not Started | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-10 | S4-T1 | Develop frontend UI | Day 11 | Day 13 | DanushAditya VC | Development | In Progress | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2
US-11 | S4-T2 | Integrate frontend with backend | Day 13 | Day 14 | DanushAditya VC | Integration | Not Started | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
US-12 | S4-T3 | End-to-end testing | Day 14 | Day 14 | DanushAditya VC | Testing | Not Started | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on overall Banking Simulator project requirements and expected features | Discussed requirements with mentor and reviewed reference banking use cases
Sprint 1 | Day 4 | Confusion in setting up project structure and Springboot server configuration | Reorganized package structure and verified Spark server setup with mentor guidance
Sprint 2 | Day 6 | Difficulty in designing Account model and repository classes | Studied sample repository patterns and refined Account class design
Sprint 2 | Day 7 | Errors while implementing deposit and withdrawal logic | Debugged logic step-by-step and added proper validations and exception handling
Sprint 2 | Day 9 | Confusion in handling account transfer dependency between multiple accounts | Implemented transfer logic using account lookup and balance checks
Sprint 3 | Day 12 | Issues while implementing low balance alert service | Reviewed alert workflow and tested threshold logic with sample accounts
Sprint 4 | Day 16 | Difficulty integrating frontend with backend APIs | Tested APIs using Postman and corrected request/response mappings
Sprint 4 | Day 18 | Minor issues during end-to-end testing of transactions | Performed repeated test cases and fixed edge-case bugs

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 01/12/2025 | 12/12/2025 | DanushAditya VC | Reviewing requirements and API design before implementation | Starting development without clear requirement confirmation | Maintaining proper documentation and planning | Adopted requirement review checklist before coding
2 | Sprint 2 | 15/12/2025 | 19/12/2025 | DanushAditya VC | Writing validations and exception handling early | Skipping edge-case testing during initial development | Using modular service-based design | Added validation checklist for all transaction flows
3 | Sprint 3 | 22/12/2025 | 02/01/2026 | DanushAditya VC | Monitoring balance thresholds during testing | Hardcoding alert values during development | Using configurable constants for alerts | Moved alert thresholds to configuration file
4 | Sprint 4 | 05/01/2026 | 16/01/2026 | DanushAditya VC | Testing frontend and backend together | Delaying integration testing until end | Using API testing tools before UI integration | Integrated Postman testing into daily workflow
5 | Sprint 4 | 19/01/2026 | 23/01/2026 | DanushAditya VC | Performing complete end-to-end test scenarios | Deploying changes without full regression testing | Executing regression test cases after changes | Created regression test checklist